## Implementation Report
TherAssist — Clinical Feedback Implementation Report (Phases 1-5)
Project: brk-prj-salvador-dura-bern-sbx ¦ Environment: DEV (gcaimh-ther-assist-DEV/) ¦ Date: February 20, 2026
Task ID | Task Name (Meeting Reference) | From Who | Original Issue (GAP) | What Was Added | Where It Was Added | What It Does Now | How It Does It | File Location | Function / Code Reference | Type
Phase 1: Safety & Edge Case Handling
1A | Deterministic Safety Keyword Scanner (James: 'risk management for edge cases') | James | System relied 100% on the LLM to catch safety concerns. If the LLM hallucinated or missed a keyword, no safety alert would fire. There was zero deterministic fallback — the entire safety system was probabilistic. | New deterministic keyword scanner function that runs on EVERY transcript segment BEFORE the LLM call. Covers 5 clinical categories (suicidal ideation, violence/homicide, abuse/mandatory reporting, substance crisis, self-harm) with ~40 keywords total. Fixed 'meth' substring false positive by requiring word-boundary matching. | Backend: main.py (lines 720-788) Constants: constants.py (lines 35-173) | Every transcript segment is scanned by a hard-coded keyword detector BEFORE reaching the AI model. If any safety keyword matches, the system: (1) forces non-strict prompt mode, (2) escalates thinking_budget to maximum (24,576 tokens), (3) injects a safety flag into the prompt, and (4) creates a deterministic alert even if the LLM returns nothing. | Uses Python regex with word-boundary matching (\b) to scan transcript text against 5 category-specific keyword lists. Each category has its own list (e.g., suicidal: 'kill myself', 'end my life', 'suicidal'; violence: 'hurt them', 'kill him', 'weapon'). Returns a SafetyScanResult dict with matched categories, keywords found, and severity. Runs in <1ms per segment. | main.py (detect_safety_keywords function, lines 720-788) constants.py (SAFETY_KEYWORDS dict, lines 35-173) | detect_safety_keywords(text: str) -> dict SAFETY_KEYWORDS = { 'suicidal_ideation': [...], 'violence_homicide': [...], 'abuse_mandatory_reporting': [...], 'substance_crisis': [...], 'self_harm': [...] } | New Feature
1B | Expanded LLM Safety Prompts (James: 'homicide, violence, abuse, substances, mandatory reporting') | James | LLM prompts only mentioned suicidal ideation. No instructions for violence toward others, child/elder abuse mandatory reporting, substance crisis, or crisis resource delivery. The AI had no guidance for 4 out of 5 safety categories. | Expanded both REALTIME_ANALYSIS_PROMPT and COMPREHENSIVE_ANALYSIS_PROMPT with explicit instructions for all 5 safety categories. Added SAFETY_CLINICAL_RESPONSES dictionary with per-category clinical protocols, crisis resources, immediate actions, and contraindications. | Backend constants: constants.py (lines 78-173, 196-335) | The AI model receives detailed instructions for handling every safety category: suicidal ideation (C-SSRS protocol), violence/homicide (Tarasoff duty-to-warn), abuse (mandatory reporting statutes), substance crisis (SAMHSA protocols), and self-harm (safety planning). Each category includes specific crisis resources (988 Lifeline, 911, Childhelp National Hotline, SAMHSA Helpline). | SAFETY_CLINICAL_RESPONSES dict maps each category to: protocol_name (e.g., 'C-SSRS', 'Tarasoff'), crisis_resources (phone numbers/URLs), immediate_actions (clinical steps), and contraindications (what NOT to do). These are injected into LLM prompts when safety keywords are detected, providing structured clinical guidance. | constants.py (SAFETY_CLINICAL_RESPONSES dict, lines 196-335) constants.py (REALTIME_ANALYSIS_PROMPT update, lines 78-173) | SAFETY_CLINICAL_RESPONSES = { 'suicidal_ideation': { protocol: 'C-SSRS', resources: ['988 Lifeline'] }, 'violence_homicide': { protocol: 'Tarasoff', resources: ['911'] }, ... } | Upgrade
1C | Enhanced Safety Alert UI Banner (James: 'therapist needs clear visual alert with crisis resources') | James | Safety alerts displayed as regular orange chips in the guidance tab — identical to routine clinical suggestions. No special visual treatment, no crisis resource display, no acknowledgment flow. Easy to miss during a live therapy session. | Full-width red SafetyAlertBanner component at the top of the session view. Includes alert title, descriptive message, crisis phone numbers, and a mandatory 'Acknowledge' button. Banner persists until therapist clicks Acknowledge. Added crisis_resources field to Alert type and SafetyScanResult interface. | Frontend: NewTherSession.tsx (banner JSX + state) types.ts (new interface fields) | When a safety alert fires, a prominent red banner appears at the TOP of the therapist's session view — impossible to miss. It shows: the alert category (e.g., 'Suicidal Ideation Detected'), the clinical message, relevant crisis phone numbers (988, 911, Childhelp, SAMHSA), and an 'Acknowledge' button. The banner persists and cannot be dismissed until acknowledged. | React component renders conditionally when safetyAlert state is non-null. Uses MUI Alert component with severity='error' and custom red styling. crisis_resources array renders as clickable phone links. Acknowledge button sets safetyAlert state to null. State is lifted to NewTherSession parent component for persistence across tab switches. | NewTherSession.tsx (SafetyAlertBanner JSX, ~30 lines) types.ts (crisis_resources?: string[] field added to Alert type) | SafetyAlertBanner component New fields: Alert.crisis_resources?: string[] SafetyScanResult interface in types.ts | New Feature
1E | Edge Case Safety Test Scripts (James + Team: 'validate safety system for edge cases') | James + Team | Only had 2 generic test transcripts (IPT→BA transitions). No safety-focused test scenarios. No way to systematically validate if the keyword scanner + LLM prompts fire correctly for crisis content across all 5 categories. | 4 new test transcript JSON files simulating realistic therapy sessions that escalate into safety concerns. Each script is a JSON array of {speaker, text} entries loadable via the 'Upload Script' button in the session view. | Test scripts directory: gcaimh-ther-assist-DEV/test-scripts/ (4 new JSON files) | Clinical team can load any of these scripts into a test session to verify the safety system fires correctly. Each script simulates a realistic therapeutic conversation that gradually escalates into a crisis scenario, testing both the keyword scanner and LLM safety detection. | JSON arrays of {speaker: 'therapist'¦'patient', text: '...'} entries. Loaded via Upload Script button → fed through transcript pipeline → triggers detect_safety_keywords() → sends to LLM with safety prompts → should produce safety alerts with crisis resources. Scripts: 1. safety_suicidal_ideation.json — Active SI with plan + means access 2. safety_abuse_disclosure.json — Child abuse/DV mandatory reporting 3. safety_violence_homicide.json — Homicidal ideation toward specific person 4. safety_substance_crisis.json — Overdose/withdrawal crisis | test-scripts/safety_suicidal_ideation.json test-scripts/safety_abuse_disclosure.json test-scripts/safety_violence_homicide.json test-scripts/safety_substance_crisis.json | Each file: JSON array of ~20-30 speaker/text entries Format: [{"speaker": "therapist", "text": "..."}, {"speaker": "patient", "text": "..."}] | New Feature
Phase 2: Therapy Modality Restructuring
2A | RAG Routing Hierarchy Restructure (CBT Umbrella) (Amy: 'CBT should be umbrella containing EBT+CBT+BA') | Amy | MODALITY_RAG_MAP mapped each modality to a single RAG datastore. CBT only pulled from cbt-corpus, not the related ba-corpus or ebt-corpus. No multi-corpus support — selecting one modality queried only one datastore, missing relevant literature from related approaches. | Changed MODALITY_RAG_MAP values from single tools to LISTS of tools. CBT/BA umbrella now pulls from ebt-corpus + cbt-corpus + ba-corpus simultaneously. Updated get_rag_tools_for_session() to iterate over tool lists with deduplication. Updated comprehensive analysis fallback. | Backend: main.py (lines 367-416, logging blocks, fallback tools) | When therapist selects CBT or BA, the system queries 3 RAG datastores simultaneously (EBT + CBT + BA). DBT queries EBT + DBT. IPT queries EBT + IPT. This ensures comprehensive literature coverage across related therapeutic approaches. Full mapping: CBT → [ebt, cbt, ba] BA → [ebt, cbt, ba] Exposure → [ebt, cbt] DBT → [ebt, dbt] IPT → [ebt, ipt] ACT → [ebt, cbt] General → [ebt, cbt] | MODALITY_RAG_MAP dict values changed from single tool references to Python lists. get_rag_tools_for_session() iterates the list, deduplicates (using set), and returns combined tool list. Logging dynamically builds corpus name strings from the active tool list. Comprehensive analysis fallback includes BA corpus for broader coverage. | main.py (MODALITY_RAG_MAP dict, lines 367-390) main.py (get_rag_tools_for_session(), lines 391-416) | MODALITY_RAG_MAP = { 'cbt': [ebt_tool, cbt_tool, ba_tool], 'ba': [ebt_tool, cbt_tool, ba_tool], 'dbt': [ebt_tool, dbt_tool], ... } get_rag_tools_for_session(session_type) -> list[Tool] | Modification
2B | Therapist Modality Selection Dialog (Team: 'therapist should explicitly choose therapy type at session start') | Team Consensus | Session started recording immediately when therapist clicked 'Start Session'. Modality was auto-inferred from the patient's focusTopics field — therapist had no input. If focusTopics was wrong or generic, the wrong RAG corpus loaded for the entire session. | Session Setup Dialog (MUI Dialog) that gates the 'Start Session' flow. Before recording begins, therapist sees 7 radio options (CBT, DBT, IPT, ACT, Exposure, BA, General) with clinical descriptions. Selected modality locks sessionContext.session_type and sets therapist_selected_modality flag. | Frontend: NewTherSession.tsx (dialog state, MODALITY_OPTIONS array, handleConfirmSessionStart) types.ts (new field) | When therapist clicks 'Start Session', a modal dialog appears BEFORE recording begins. The dialog presents 7 therapy modalities with brief descriptions (e.g., 'CBT — Cognitive Behavioral Therapy: Structured approach focusing on thoughts, feelings, and behaviors'). Therapist selects one, clicks 'Confirm', and THEN recording starts. A blue 'Therapist Selected' badge displays throughout the session. | MUI Dialog component with RadioGroup. MODALITY_OPTIONS constant array holds {value, label, description} for each modality. handleConfirmSessionStart() sets sessionContext.session_type to selected value, sets therapist_selected_modality: true, closes dialog, and initiates recording. The flag prevents AI from overriding the therapist's explicit choice. | NewTherSession.tsx (SessionSetupDialog, ~80 lines) NewTherSession.tsx (MODALITY_OPTIONS array) types.ts (therapist_selected_modality: boolean) | MODALITY_OPTIONS = [{value: 'cbt', label: 'CBT', description: '...'}, ...] handleConfirmSessionStart(selectedModality: string) therapist_selected_modality field in SessionContext type | New Feature
2C | Disable Mid-Session Modality Auto-Switching (Team: 'avoid switch in session between therapy types') | Team Consensus | When the AI detected a different modality at >=70% confidence mid-session, it silently changed sessionContext.session_type — switching RAG corpus mid-conversation. Therapist might not notice. Clinically disruptive: RAG citations suddenly change from CBT to DBT literature without therapist consent. | Removed the auto-switch code block. AI-detected modality now stored in sessionMetrics.detected_modality for display only. Three-state display system: 'Therapist Selected' (blue badge), 'AI suggests: X' (amber chip), or 'Gathering data...' (grey chip). | Frontend: NewTherSession.tsx (replaced auto-switch block, updated chip rendering) | The system NEVER automatically switches therapy modality mid-session. The therapist's explicit selection (from Task 2B) is locked for the entire session. The AI's modality detection still runs but is display-only: shown as an amber 'AI suggests: X (Y%)' chip that the therapist can note for future sessions. Three visual states: (1) Blue badge = therapist selected, (2) Amber chip = AI suggestion differs, (3) Grey chip = gathering data. | Deleted the conditional block (old lines 493-508) that called setSessionContext when AI confidence >= 70%. AI detection result now writes to sessionMetrics.detected_modality (read-only). Chip rendering logic uses conditional: if therapist_selected_modality → show blue badge; else if detected != selected AND words >= threshold → show amber chip; else → show grey 'Gathering data' chip. | NewTherSession.tsx (removed auto-switch block) NewTherSession.tsx (updated modality chip rendering) | Removed: if (confidence >= 0.7) setSessionContext({session_type: detected}) Added: sessionMetrics.detected_modality = detected (display-only) Three-state chip rendering logic | Modification
2E | Minimum Transcript Threshold for Modality Detection (Team: 'suggestion should be based on enough transcript') | Team Consensus | AI would suggest a modality after just 1-2 transcript entries (~30 words). Not clinically meaningful — insufficient therapeutic content for reliable modality detection. Resulted in noisy, low-confidence suggestions that changed frequently in early session. | Word count tracking (totalWordCountRef) across all transcript entries. MIN_WORDS_FOR_MODALITY_SUGGESTION = 200 (~2-3 minutes of conversation). Frontend suppresses modality suggestion display until threshold met. Backend has matching constant. | Frontend: NewTherSession.tsx (word counting + threshold guard) Backend: constants.py (MIN_WORDS constant) | The system waits until at least 200 words of transcript have been accumulated (~2-3 minutes of conversation) before displaying any AI modality suggestion. Until then, a grey 'Gathering data...' chip is shown. This ensures the AI has enough therapeutic content to make a clinically meaningful modality assessment. | totalWordCountRef (React useRef) increments on every transcript entry from 3 sources: finalized microphone transcripts, test transcript entries, and transcript playback. Split by whitespace, count words, accumulate. Modality chip rendering checks: if totalWordCountRef.current < MIN_WORDS_FOR_MODALITY_SUGGESTION → show 'Gathering data...' chip. Resets to 0 on new session start. | NewTherSession.tsx (totalWordCountRef, word counting logic) constants.py (MIN_WORDS_FOR_MODALITY_DETECTION = 200) | totalWordCountRef = useRef<number>(0) MIN_WORDS_FOR_MODALITY_SUGGESTION = 200 MIN_WORDS_FOR_MODALITY_DETECTION = 200 (backend) | New Feature
Phase 3: Evaluation & Data Pipeline
3B | Wire TherSummary to Live Session Data (Team: 'evaluate real session summaries, not hardcoded demo data') | Team | TherSummary.tsx rendered with hardcoded defaults: 'John Doe', 41 min duration, 18 techniques. The component had prop interfaces for real data but App.tsx never passed it. When a session ended, the summary always showed fake placeholder data regardless of what the AI generated. | Full data pipeline from session end to summary view. Added lastSessionSummary state in App.tsx. Expanded handleSessionSaved callback. Mapped SessionSummary fields to TherSummary props: progress_indicators, areas_for_improvement, follow_up_recommendations, homework_assignments (with title/description/reference mapping), risk_assessment.level with color-coded display. | Frontend: App.tsx (state, callback, rendering) NewTherSession.tsx (onSessionSaved call + prop type) | When a session ends and the AI generates a comprehensive summary, ALL real data flows through to the TherSummary view: actual progress indicators, real areas for improvement, AI-generated follow-up recommendations, homework assignments with clinical references, and color-coded risk assessment level. Falls back gracefully to defaults if no AI summary is available. | App.tsx: lastSessionSummary useState stores SessionSummary from completed session. handleSessionSaved callback receives fullSummary parameter from NewTherSession. Mapping layer converts backend SessionSummary shape to TherSummary prop shape (e.g., homework_assignments[].title → homeworkTitle, .description → homeworkDesc, .reference → homeworkRef). Risk level maps to color: 'low' → green, 'moderate' → amber, 'high' → red. | App.tsx (lastSessionSummary state, handleSessionSaved, rendering) NewTherSession.tsx (onSessionSaved fullSummary parameter) | lastSessionSummary = useState<SessionSummary ¦ null>(null) handleSessionSaved(sessionId, patientId, fullSummary?: SessionSummary) Prop mapping: summary.homework_assignments → TherSummary homework props | Modification
Phase 5: Safety RAG & Patient Interface
5A | Safety & Crisis RAG Document Corpus (Clinical team: evidence- based safety protocols for AI grounding) | Clinical Team | The AI safety system had no evidence-based clinical literature to ground its responses. Safety alerts and crisis guidance were generated from LLM training data only — not from authoritative clinical protocols like C-SSRS, SAMHSA guidelines, or mandatory reporting standards. | 9 open-access clinical PDF documents downloaded and ingested into a new 'safety-crisis' Vertex AI Search datastore. New SAFETY_RAG_TOOL always included in every session's tool list (not modality-dependent). Setup script created for reproducible deployment. | GCP: safety-crisis datastore GCS: brk-prj-salvador-dura-bern-sbx-safety-crisis bucket Backend: main.py (SAFETY_RAG_TOOL) Setup: setup_services/rag/ | Every therapy session — regardless of modality — has access to evidence-based safety and crisis literature. When the AI detects safety concerns, it can ground its recommendations in authoritative clinical protocols (C-SSRS screening criteria, SAMHSA crisis care guidelines, Stanley-Brown safety planning, mandatory reporting statutes) rather than relying solely on training data. | 9 PDFs uploaded to GCS bucket → imported into Vertex AI Search datastore 'safety-crisis'. SAFETY_RAG_TOOL defined using Vertex AI genai Tool class pointing to the datastore. Tool is appended to every session's tool list in get_rag_tools_for_session() regardless of selected modality. AI model can cite specific passages from these documents in its safety guidance. Documents: - C-SSRS Baseline Screening & Full Baseline - 988 Lifeline Risk Assessment Standards & Safety Policy - SAMHSA National Guidelines for Crisis Care - SAMHSA SAFE-T Suicide Assessment - SAMHSA TIP50 (Suicidal Thoughts + Substance Abuse) - Stanley-Brown Safety Plan - Child Welfare Mandatory Reporting Statutes | setup_services/rag/corpus_safety/ (9 PDF files) setup_services/rag/setup_safety_datastore.py main.py (SAFETY_RAG_TOOL definition + inclusion) | SAFETY_RAG_TOOL = Tool.from_retrieval( retrieval=Retrieval(source=VertexAISearch( datastore='safety-crisis'))) Always included: tools.append(SAFETY_RAG_TOOL) | New Feature
5B | Session History for Modality Recommendation (Team: 'base therapy type on previous sessions') | Team Consensus | The modality selection dialog (Task 2B) pre-selects based on patient's focusTopics field, but has no knowledge of what therapy modalities were used in previous sessions. Therapist must remember past session types from memory. | BLOCKED — Requires Firebase/Firestore read permissions that are not currently available in the dev environment. Implementation plan ready: backend endpoint get_patient_session_history to fetch last 3 sessions, frontend useEffect to display 'Previous sessions: CBT (2), BA (1)' in setup dialog. | N/A — Blocked on Firebase permissions | Currently NOT implemented. The modality selection dialog pre-selects based on patient focusTopics (existing behavior). Once Firebase access is granted, will show session history recommendations above the modality radio buttons. | Planned: Backend queries Firestore for patient's last 3 session documents, extracts session_type field, counts frequency. Returns {modalities: [{type: 'cbt', count: 2, last_date: '...'}, ...]}. Frontend fetches on dialog open, displays as recommendation chip above radio buttons, pre-selects most frequent modality. | Planned: main.py (get_patient_session_history endpoint) NewTherSession.tsx (useEffect fetch in dialog) | Planned: get_patient_session_history(patient_id) -> dict Frontend: useEffect(() => fetchHistory(patientId), [patientId]) | Blocked (Planned Feature)
5C | Patient Post-Session Interface (Team: 'patient-facing summary view') | Team / Tarek | No patient-facing view existed. The TherSummary component showed clinical-internal data (risk levels, technique counts, clinical citations, therapist notes) that is inappropriate for patient viewing. Patients had no way to review homework or session takeaways. | New PatientSummary.tsx component with simplified, patient-friendly display. New route in App.tsx. New backend endpoint get_patient_summary returning filtered data subset (no risk assessment, no clinical citations). 'View Patient Summary' button added to TherSummary. | Frontend: PatientSummary.tsx (NEW) App.tsx (new route + view) TherSummary.tsx (button) Backend: main.py (get_patient_summary) | After a session, therapist can click 'View Patient Summary' to see what the patient would see. The patient view shows: session date/duration, homework assignments with interactive checkboxes, progress highlights (framed positively), follow-up recommendations in plain language, and next session reminders. It strips out: risk levels, technique counts, clinical citations, and therapist-only notes. | PatientSummary.tsx reuses TherSummary data model but filters and reformats. Homework displayed as cards with checkboxes (task + rationale, no manual references). Progress indicators use encouraging language. Backend get_patient_summary action filters SessionSummary to remove clinical-internal fields before returning. Route '/patient-summary' in App.tsx renders the component with passed data. | frontend/components/PatientSummary.tsx (NEW, ~200 lines) frontend/components/App.tsx (route + navigation) frontend/components/TherSummary.tsx (button) backend/therapy-analysis-function/main.py (get_patient_summary) | PatientSummary component (React functional component) get_patient_summary(session_id) -> filtered dict App.tsx: case 'patientSummary': <PatientSummary ... /> TherSummary: onViewPatientSummary callback | New Feature

## RAG & Corpus Reference
RAG Datastores & Corpus Reference
RAG Datastore Name | Corpus Directory | Content Description | # Documents | Modalities Using It
ebt-corpus | corpus_ebt | Evidence-Based Treatment manuals (PE, CBT-Social Phobia, Deliberate Practice) | ~5 | ALL modalities (base corpus)
cbt-corpus | corpus_cbt | 31 CBT randomized controlled trials and clinical studies | 31 | CBT, BA, Exposure, ACT, General
ba-corpus | corpus_ba | 11 Behavioral Activation treatment studies | 11 | CBT, BA
dbt-corpus | corpus_dbt | 6 DBT randomized controlled trials and systematic reviews | 6 | DBT
ipt-corpus | corpus_ipt | 10 IPT randomized controlled trials and meta-analyses | 10 | IPT
transcript-patterns | corpus_transcripts | Beck Institute sessions + ThousandVoicesOfTrauma therapy dataset | ~10 | Pattern matching (all)
safety-crisis | corpus_safety | Clinical safety protocols, crisis guidelines, mandatory reporting (see below) | 9 | ALL sessions (always included)
Safety RAG Corpus Documents (safety-crisis datastore)
Document Name (PDF) | Source Organization | Clinical Use
C-SSRS_Baseline_Screening.pdf | Columbia University (cssrs.columbia.edu) | Suicide risk screening — baseline questions
C-SSRS_Full_Baseline.pdf | Columbia University (cssrs.columbia.edu) | Full Columbia Suicide Severity Rating Scale
988_Lifeline_Suicide_Risk_Assessment_Standards.pdf | 988 Suicide & Crisis Lifeline | Risk assessment best practices for crisis counselors
988_Lifeline_Suicide_Safety_Policy.pdf | 988 Suicide & Crisis Lifeline | Safety policy for suicide crisis intervention
SAMHSA_National_Guidelines_Crisis_Care.pdf | SAMHSA (US Gov, public domain) | National guidelines for behavioral health crisis care
SAMHSA_SAFE-T_Suicide_Assessment.pdf | SAMHSA (US Gov, public domain) | Suicide Assessment Five-step Evaluation and Triage
SAMHSA_TIP50_Suicidal_Thoughts_Substance_Abuse.pdf | SAMHSA (US Gov, public domain) | Addressing suicidal thoughts in substance abuse treatment
Stanley-Brown_Safety_Plan.pdf | Stanley & Brown (open clinical use) | Safety Planning Intervention template and guide
ChildWelfare_Mandatory_Reporting_Statutes.pdf | Children's Bureau (childwelfare.gov, US Gov) | State-by-state mandatory reporting statutes for child abuse